## Ballots-Summary_1
WI Responsible body name | WI Responsible body secretariat | WI number | Project ID | Standard nature | Standard reference | Standard title | Launching of ballot | Closing of ballot
CEN/CLC/JTC 13 | DIN | JT013090 | 81343 | EN | prEN 40000-1-3 | Cybersecurity requirements for products with digital elements - Part 1-3: Vulnerability Handling | 2025-12-11 | 2026-03-05
CEN/TC 256 | DIN | 00256A2O | 76296 | EN | prEN 17833 | Railway applications - Simulation Credibility | 2026-01-15 | 2026-04-09
CEN/TC 107 | DS | 00107099 | 81183 | EN | prEN 17248 | District heating and district cooling pipe systems - Terms and definitions | 2026-01-15 | 2026-04-09
CEN/TC 260 | DIN | 00260207 | 68251 | EN | prEN 12944-1 | Fertilizers, liming materials and inhibitors - Vocabulary - Part 1: General terms | 2026-01-22 | 2026-04-16
CEN/TC 260 | DIN | 00260208 | 68254 | EN | prEN 12944-2 | Fertilizers, liming materials and inhibitors - Vocabulary - Part 2: Terms relating to fertilizers | 2026-01-22 | 2026-04-16
CEN/TC 275 | DIN | 00275388 | 81468 | EN | prEN 15634-6 | Foodstuffs - Detection of food allergens by molecular biological methods - Part 6: Wheat (Triticum L.) and Rye (Secale cereale) - Qualitative detection of a specific DNA sequence in cooked sausages by real-time PCR | 2026-01-22 | 2026-04-16
CEN/TC 275 | DIN | 00275389 | 81469 | EN | prEN 15634-7 | Foodstuffs - Detection of food allergens by molecular biological methods - Part 7: Peanut (Arachis hypogaea) - Qualitative detection of a specific DNA sequence in food by real-time PCR | 2026-01-22 | 2026-04-16
CEN/TC 275 | DIN | 00275390 | 81470 | EN | prEN 15634-8 | Foodstuffs - Detection of food allergens by molecular biological methods - Part 8: Peanut (Arachis hypogaea), hazelnut (Corylus spp.), walnut (Juglans regia) and cashew (Anacardium occidentale) - Qualitative detection of specific DNA sequences in food by real-time PCR | 2026-01-22 | 2026-04-16
CEN/TC 275 | DIN | 00275391 | 81471 | EN | prEN 15634-9 | Foodstuffs - Detection of food allergens by molecular biological methods - Part 9: Fish - Qualitative detection of a specific DNA sequence in food by real-time PCR | 2026-01-22 | 2026-04-16
CEN/TC 224 | AFNOR | 00224280 | 77621 | TS | FprCEN/TS 18212-5 | Personal identification - Requirements for biometric products - Part 5: Face biometrics | 2026-01-29 | 2026-04-23
CEN/TC 156 | BSI | 00156301 | 79757 | EN | prEN 18289 | Ventilation for buildings - Metallic ventilation ducts - Requirements and test methods | 2026-01-29 | 2026-04-23
CEN/TC 447 | BSI | 00447005 | 76806 | EN | prEN 18306 | Provision of services - Guidance for organizations which provide lists of prequalified, qualified or shortlisted service providers | 2026-01-29 | 2026-04-23
CEN/TC 440 | DIN | 00440024 | 79785 | EN | prEN 17014-1 | Electronic public procurement - Pre-award - Part 1: Choreographies | 2026-01-29 | 2026-04-23
CEN/TC 440 | DIN | 00440025 | 79786 | EN | prEN 17014-2 | Electronic public procurement - Pre-award - Part 2: Transactions | 2026-01-29 | 2026-04-23
CEN/TC 107 | DS | 00107100 | 81193 | TR | FprCEN/TR 18341 | District heating and cooling systems - Supplementary information on usage of CEN/TC 107 documents | 2026-02-05 | 2026-04-30

## Overview & Work Programme_2
WI Responsible body name | WI Responsible body secretariat | WI number | Project ID | Standard reference | English title | Last realized milestone name | Last realized milestone stagecode | Int rel | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Public comment
CEN/TC 247 | SNV | 00247150 | 83331 |  | Standardised process and competencies for on-site assessments of Smart Readiness Indicator (SRI) for buildings | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-01-15 | 2026-01-15 | 30.99.0979 |  | 2027-01-23 | [9 empty] | 50.20.0000 |  | 2027-04-26 | 50.60.0000 |  | 2027-07-19 | 60.55.0000 |  | 2027-08-16 | 60.60.0000 |  | 2027-09-13
CEN/TC 264 | DIN | 00264233 | 76800 | prEN XXX | Ambient air quality - Diffusive samplers for the determination of concentrations of gases - Requirements, validation methods and use | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-07-02 | 2025-07-02 | 30.99.0979 |  | 2026-04-30 | 40.20.0000 |  | 2026-07-30 | 40.60.0000 |  | 2026-10-22 | 45.99.0979 |  | 2027-04-14 | 50.20.0000 |  | 2027-06-23 | 50.60.0000 |  | 2027-08-18 | 60.55.0000 |  | 2027-09-15 | 60.60.0000 |  | 2027-10-13 | 2025-07-09: OSD
CEN/TC 89 | SIS | 00089203 | 72866 | prEN 12939 | Thermal performance of building materials and products - Determination of thermal resistance by means of guarded hot plate and heat flow meter methods - Thick products of high and medium thermal resistance | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-11-17 | 2024-11-17 | 30.99.0979 | 2025-07-08 | 2025-07-08 | 40.20.0000 | 2025-10-16 | 2025-10-16 | 40.60.0000 | 2026-01-08 | 2026-01-08 | 45.99.0979 |  | 2026-08-30 | 50.20.0000 |  | 2026-11-09 | 50.60.0000 |  | 2027-01-04 | 60.55.0000 |  | 2027-02-01 | 60.60.0000 |  | 2027-03-01 | OSD
CEN/TC 137 | DIN | 00137092 | 76136 | prEN XXX | Workplace exposure - Measurement of viruses in workplace air | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-08-01 | 2025-08-01 | 30.99.0979 |  | 2026-05-01 | 40.20.0000 |  | 2026-07-31 | 40.60.0000 |  | 2026-10-23 | 45.99.0979 |  | 2027-01-01 | 50.20.0000 |  | 2027-03-12 | 50.60.0000 |  | 2027-05-07 | 60.55.0000 |  | 2027-06-04 | 60.60.0000 |  | 2027-07-02 | OSD
CEN/TC 155 | NEN | 00155A2H | 82112 | prCEN/TS 14758-2 rev | Plastics piping systems for non‐pressure underground drainage and sewerage - Polypropylene with mineral modifiers (PP‐MD) - Part 2: Assessment of conformity | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-06-04 | 2025-06-04 | 30.99.0979 |  | 2026-06-04 | [9 empty] | 50.20.0000 |  | 2026-09-03 | 50.60.0000 |  | 2026-11-26 | 60.55.0000 |  | 2026-12-24 | 60.60.0000 |  | 2027-01-21 | 2025-06-12: OSD
CEN/TC 224 | AFNOR | 00224294 | 83513 |  | Personal identification — Developing and maintaining the risk register for EUDI Wallet implementation and certification | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-17 | 2026-02-17 | 30.99.0979 |  | 2026-07-28 | [9 empty] | 50.20.0000 |  | 2026-10-27 | 50.60.0000 |  | 2027-01-19 | 60.55.0000 |  | 2027-02-16 | 60.60.0000 |  | 2027-03-16 | OSD
CEN/TC 261 | AFNOR | 00261549 | 82674 | prCEN/TS XXX | Packaging — Design for recycling — Part 2: Testing protocol for textile packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-18 | 2025-09-18 | 30.99.0979 |  | 2025-12-31 | [9 empty] | 50.20.0000 |  | 2026-04-01 | 50.60.0000 |  | 2026-06-24 | 60.55.0000 |  | 2026-07-22 | 60.60.0000 |  | 2026-08-19 | 2025-09-24:OSD
CEN/TC 473 | SIS | 00473001 | 80616 | prCEN/TS XXX | Circular economy - Guidance on the implementation of ISO 59010 with consideration of European policies and regulations | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-09-10 | 2024-09-10 | 30.99.0979 |  | 2026-06-09 | [9 empty] | 50.20.0000 |  | 2026-09-08 | 50.60.0000 |  | 2026-12-01 | 60.55.0000 |  | 2027-01-04 | 60.60.0000 |  | 2027-02-01 | OSD
CEN/TC 261 | AFNOR | 00261547 | 82557 | FprCEN/TS XXXX-2 | Packaging - Design for recycling - Part 2: Testing protocol for wood packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-29 | 2025-08-29 | 30.99.0979 |  | 2025-11-03 | [9 empty] | 50.20.0000 |  | 2026-02-02 | 50.60.0000 |  | 2026-04-27 | 60.55.0000 |  | 2026-05-26 | 60.60.0000 |  | 2026-06-23 | 2025-10-13: OSD
CEN/CLC/JTC 14 | UNI | JT014023 | 78471 | prEN XXX | Values and Benefits of Decarbonisation and Energy Performance Actions - A General Framework for Assessment | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-16 | 2025-04-16 | 30.99.0979 |  | 2026-02-18 | 40.20.0000 |  | 2026-05-20 | 40.60.0000 |  | 2026-08-12 | 45.99.0979 |  | 2027-01-27 | 50.20.0000 |  | 2027-04-07 | 50.60.0000 |  | 2027-06-02 | 60.55.0000 |  | 2027-06-30 | 60.60.0000 |  | 2027-07-28 | 2025-10-31: OSD
CEN/TC 468 | AFNOR | 00468001 | 76347 |  | Mapping of existing standardization deliverables on European digital archiving and preservation | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2022-07-04 | 2022-07-04 | 30.99.0979 |  | 2023-05-30 | [9 empty] | 50.20.0000 |  | 2023-07-04 | 50.60.0000 |  | 2023-09-26 | 60.55.0000 |  | 2023-10-10 | 60.60.0000 |  | 2023-10-24 | 2026-01-20: OSD
CEN/CLC/JTC 22 | DIN | JT022014 | 82412 | prCEN/CLC/TR XXX | Gaps in IT security evaluation of QKD systems and networks | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-07-24 | 2025-07-24 | 30.99.0979 |  | 2026-09-01 | [9 empty] | 50.20.0000 |  | 2026-10-06 | 50.60.0000 |  | 2027-01-04 | 60.55.0000 |  | 2027-01-18 | 60.60.0000 |  | 2027-02-01 | 2025-08-05: OSD
CEN/TC 89 | SIS | 00089198 | 72855 | prEN 12667 | Thermal performance of building materials and products - Determination of thermal resistance by means of guarded hot plate and heat flow meter methods - Products of high and medium thermal resistance | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-11-17 | 2024-11-17 | 30.99.0979 | 2025-07-08 | 2025-07-08 | 40.20.0000 | 2025-10-16 | 2025-10-16 | 40.60.0000 | 2026-01-08 | 2026-01-08 | 45.99.0979 |  | 2026-08-30 | 50.20.0000 |  | 2026-11-09 | 50.60.0000 |  | 2027-01-04 | 60.55.0000 |  | 2027-02-01 | 60.60.0000 |  | 2027-03-01 | OSD
CEN/TC 275 | DIN | 00275390 | 81470 | prEN 15634-8 | Foodstuffs - Detection of food allergens by molecular biological methods - Part 8: Peanut (Arachis hypogaea), hazelnut (Corylus spp.), walnut (Juglans regia) and cashew (Anacardium occidentale) - Qualitative detection of specific DNA sequences in food by real-time PCR | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2025-02-20 | 2025-02-20 | 30.99.0979 | 2025-10-17 | 2025-10-17 | 40.20.0000 | 2026-01-22 | 2026-01-22 | 40.60.0000 |  | 2026-04-16 | 45.99.0979 |  | 2026-12-03 | 50.20.0000 |  | 2027-02-11 | 50.60.0000 |  | 2027-04-08 | 60.55.0000 |  | 2027-05-06 | 60.60.0000 |  | 2027-06-03 | 2025-03-04: OSD
CEN/TC 89 | SIS | 00089201 | 72858 | prEN 12664 | Thermal performance of building materials and products - Determination of thermal resistance by means of guarded hot plate and heat flow meter methods - Dry and moist products of medium and low thermal resistance | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-11-14 | 2024-11-14 | 30.99.0979 | 2025-07-08 | 2025-07-08 | 40.20.0000 | 2025-10-16 | 2025-10-16 | 40.60.0000 | 2026-01-08 | 2026-01-08 | 45.99.0979 |  | 2026-08-27 | 50.20.0000 |  | 2026-11-05 | 50.60.0000 |  | 2027-01-04 | 60.55.0000 |  | 2027-02-01 | 60.60.0000 |  | 2027-03-01 | OSD
CEN/TC 162 | DIN | 00162499 | 80770 | prEN 342 rev | Protective clothing - Ensembles and garments for protection against cold | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-10-04 | 2024-10-04 | 30.99.0979 |  | 2025-05-30 | 40.20.0000 |  | 2025-08-29 | 40.60.0000 |  | 2025-11-21 | 45.99.0979 |  | 2026-07-17 | 50.20.0000 |  | 2026-09-25 | 50.60.0000 |  | 2026-11-20 | 60.55.0000 |  | 2026-12-18 | 60.60.0000 |  | 2027-01-15 | 2025-02-18 : OSD
CEN/TC 128 | NBN | 00128207 | 78535 | prEN 18189 | Rooflights and roof hatches - Environmental Product Declarations - Complementary product category rules (cPCR) to EN 15804 | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-12-15 | 2024-12-15 | 30.99.0979 | 2025-02-17 | 2025-02-17 15:11 | 40.20.0000 | 2025-05-15 | 2025-05-15 | 40.60.0000 | 2025-08-07 | 2025-08-07 | 45.99.0979 |  | 2026-09-27 | 50.20.0000 |  | 2026-12-07 | 50.60.0000 |  | 2027-02-01 | 60.55.0000 |  | 2027-03-01 | 60.60.0000 |  | 2027-03-29 | OSD
CEN/CLC/JTC 13 | DIN | JT013097 | 82477 |  | Cybersecurity requirements for products with digital elements —Threats and Security Objectives | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-06 | 2025-08-06 | 30.99.0979 |  | 2026-08-05 | [9 empty] | 50.20.0000 |  | 2026-09-09 | 50.60.0000 |  | 2026-12-02 | 60.55.0000 |  | 2026-12-16 | 60.60.0000 |  | 2027-01-04 | OSD
CEN/TC 51 | NBN | 00051160 | 76333 | prEN 196-1 rev | Methods of testing cement - Part 1: Determination of strength | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-11-13 | 2025-11-13 | 30.99.0979 |  | 2026-07-09 | 40.20.0000 |  | 2026-10-08 | 40.60.0000 |  | 2027-01-04 | 45.99.0979 |  | 2027-08-26 | 50.20.0000 |  | 2027-11-04 | 50.60.0000 |  | 2028-01-03 | 60.55.0000 |  | 2028-01-31 | 60.60.0000 |  | 2028-02-28 | OSD
CEN/TC 406 | AFNOR | 00406006 | 83201 |  | Mechanical products — Calculating the Carbon Footprint of a Product in mechanical and plant engineering | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-12-19 | 2025-12-19 | 30.99.0979 |  | 2026-08-14 | 40.20.0000 |  | 2026-11-13 | 40.60.0000 |  | 2027-02-05 | 45.99.0979 |  | 2027-10-01 | 50.20.0000 |  | 2027-12-10 | 50.60.0000 |  | 2028-02-04 | 60.55.0000 |  | 2028-03-03 | 60.60.0000 |  | 2028-03-31 | 2025-12-23: OSD
CEN/TC 224 | AFNOR | 00224276 | 77237 | FprCEN/TS 18098 | Guidelines for the onboarding of user personal identification data within European Digital Identity Wallets | Closure of Vote on TS | 50.60.0000 | Homegrown | 10.99.0000 | 2022-12-14 | 2022-12-14 | 30.99.0979 | 2025-04-24 | 2025-04-24 | [9 empty] | 50.20.0000 | 2025-07-17 | 2025-07-17 | 50.60.0000 | 2025-10-09 | 2025-10-09 | 60.55.0000 |  | 2025-11-06 | 60.60.0000 |  | 2025-12-04 | OSD
CEN/TC 459/SC 9 | AFNOR | EC109100 | 81925 | prEN 10111 rev | Continuously hot rolled low carbon steel sheet and strip for cold forming - Technical delivery conditions | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-23 | 2026-02-23 | 30.99.0979 |  | 2026-10-19 | 40.20.0000 |  | 2027-01-18 | 40.60.0000 |  | 2027-04-12 | 45.99.0979 |  | 2027-12-06 | 50.20.0000 |  | 2028-02-14 | 50.60.0000 |  | 2028-04-10 | 60.55.0000 |  | 2028-05-09 | 60.60.0000 |  | 2028-06-06 | 2025-06-18: OSD
CEN/TC 168 | BSI | 00168153 | 77915 | prEN 1492-4 rev | Textile slings - Safety - Part 4: Lifting slings for general-purpose and engineered lifting operations made from synthetic fiber ropes | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-12 | 2026-02-12 | 30.99.0979 |  | 2026-10-08 | 40.20.0000 |  | 2027-01-07 | 40.60.0000 |  | 2027-04-01 | 45.99.0979 |  | 2027-11-25 | 50.20.0000 |  | 2028-02-03 | 50.60.0000 |  | 2028-03-30 | 60.55.0000 |  | 2028-04-27 | 60.60.0000 |  | 2028-05-25 | OSD
CEN/TC 182 | DIN | 00182096 | 73151 | prEN 378-3 | Refrigerating systems and heat pumps - Safety and environmental requirements - Part 3: Installation site and personal protection | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2023-10-27 | 2023-10-27 | 30.99.0979 | 2025-01-31 | 2025-01-31 15:47 | 40.20.0000 | 2025-07-03 | 2025-07-03 | 40.60.0000 | 2025-09-25 | 2025-09-25 | 45.99.0979 |  | 2026-05-08 | 50.20.0000 |  | 2026-07-17 | 50.60.0000 |  | 2026-09-11 | 60.55.0000 |  | 2026-10-09 | 60.60.0000 |  | 2026-11-06 | OSD
CEN/CLC/JTC 21 | DS | JT021037 | 80364 | prEN 18284 | Artificial Intelligence -- Quality and governance of datasets in AI | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-09-05 | 2024-09-05 | 30.99.0979 |  | 2026-02-01 | 40.20.0000 |  | 2026-05-04 | 40.60.0000 |  | 2026-07-27 | 45.99.0979 |  | 2027-03-18 | 50.20.0000 |  | 2027-05-27 | 50.60.0000 |  | 2027-07-22 | 60.55.0000 |  | 2027-08-19 | 60.60.0000 |  | 2027-09-16 | OSD
CEN/TC 261 | AFNOR | 00261533 | 81845 |  | Packaging — Design for recycling — Part 1: Process and design criteria to evaluate the recyclability of glass packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 202/04/28:OSD
CEN/CLC/JTC 22 | DIN | JT022011 | 81992 | prCEN/CLC/TR XXX | Standardization needs for satellite based QKD | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-16 | 2025-04-16 | 30.99.0979 |  | 2026-04-15 | [9 empty] | 50.20.0000 |  | 2026-05-20 | 50.60.0000 |  | 2026-08-12 | 60.55.0000 |  | 2026-08-26 | 60.60.0000 |  | 2026-09-09 | 2025-05-20:OSD
CEN/TC 348 | SN | 00348029 | 76860 |  | EN 15221-10 Digital Transformation of Facility Management (FM) | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-11-21 | 2025-11-21 | 30.99.0979 |  | 2026-07-17 | 40.20.0000 |  | 2026-10-16 | 40.60.0000 |  | 2027-01-08 | 45.99.0979 |  | 2027-09-03 | 50.20.0000 |  | 2027-11-12 | 50.60.0000 |  | 2028-01-07 | 60.55.0000 |  | 2028-02-04 | 60.60.0000 |  | 2028-03-03 | OSD
CEN/TC 469 | AFNOR | 00469004 | 78202 | prEN 18000-3 | Animal health diagnostic analyses - Control of in vitro diagnostic reagents - Part 3: Reagents for PCR techniques | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-06-04 | 2024-06-04 | 30.99.0979 | 2024-12-18 | 2024-12-18 16:26 | 40.20.0000 | 2025-04-03 | 2025-04-03 | 40.60.0000 | 2025-06-26 | 2025-06-26 | 45.99.0979 |  | 2026-05-27 | 50.20.0000 |  | 2026-08-05 | 50.60.0000 |  | 2026-09-30 | 60.55.0000 |  | 2026-10-28 | 60.60.0000 |  | 2026-11-25 | OSD
CEN/TC 224 | AFNOR | 00224286 | 81428 |  | Decomposition of the EUDI Wallet – Part 2: Decomposition of the Provider by Service in the objective of Functional and Security Certifications | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-02-13 | 2025-02-13 | 30.99.0979 |  | 2026-11-02 | [9 empty] | 50.20.0000 |  | 2027-02-01 | 50.60.0000 |  | 2027-04-26 | 60.55.0000 |  | 2027-05-24 | 60.60.0000 |  | 2027-06-21 | 2025-02-18: OSD
CEN/TC 447 | BSI | 00447005 | 76806 | prEN 18306 | Provision of services - Guidance for organizations which provide lists of prequalified, qualified or shortlisted service providers | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2025-10-06 | 2025-10-06 | 30.99.0979 | 2025-11-13 | 2025-11-13 | 40.20.0000 | 2026-01-29 | 2026-01-29 | 40.60.0000 |  | 2026-04-23 | 45.99.0979 |  | 2027-03-30 | 50.20.0000 |  | 2027-06-08 | 50.60.0000 |  | 2027-08-03 | 60.55.0000 |  | 2027-08-31 | 60.60.0000 |  | 2027-09-28 | 2024-01-06: OSD
CEN/TC 260 | DIN | 00260207 | 68251 | prEN 12944-1 | Fertilizers, liming materials and inhibitors - Vocabulary - Part 1: General terms | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-10-01 | 2024-10-01 | 30.99.0979 | 2025-10-28 | 2025-10-28 | 40.20.0000 | 2026-01-22 | 2026-01-22 | 40.60.0000 |  | 2026-04-16 | 45.99.0979 |  | 2026-07-15 | 50.20.0000 |  | 2026-09-23 | 50.60.0000 |  | 2026-11-18 | 60.55.0000 |  | 2026-12-16 | 60.60.0000 |  | 2027-01-13 | 2025-07-23:OSD
CEN/TC 98 | DIN | 00098063 | 82714 | prEN 1495 rev | Lifting platforms - Mast climbing work platforms | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-22 | 2025-09-22 | 30.99.0979 |  | 2026-05-18 | 40.20.0000 |  | 2026-08-17 | 40.60.0000 |  | 2026-11-09 | 45.99.0979 |  | 2027-07-05 | 50.20.0000 |  | 2027-09-13 | 50.60.0000 |  | 2027-11-08 | 60.55.0000 |  | 2027-12-06 | 60.60.0000 |  | 2028-01-03 | 2025-09-24: OSD
CEN/TC 207 | UNI | 00207320 | 80525 |  | Furniture – Circularity – Guidance on reliability | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-26 | 2025-09-26 | 30.99.0979 |  | 2026-05-22 | 40.20.0000 |  | 2026-08-21 | 40.60.0000 |  | 2026-11-13 | 45.99.0979 |  | 2027-07-09 | 50.20.0000 |  | 2027-09-17 | 50.60.0000 |  | 2027-11-12 | 60.55.0000 |  | 2027-12-10 | 60.60.0000 |  | 2028-01-07 | OSD
CEN/TC 175 | AFNOR | 00175197 | 74250 | prEN 16755 | Classes of fire-retardant treated wood products in interior and exterior end use applications - Reaction to fire performance | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-06-24 | 2024-06-24 | 30.99.0979 | 2025-02-04 | 2025-02-04 15:01 | 40.20.0000 | 2025-04-24 | 2025-04-24 | 40.60.0000 | 2025-07-17 | 2025-07-17 | 45.99.0979 |  | 2026-04-06 | 50.20.0000 |  | 2026-06-15 | 50.60.0000 |  | 2026-08-10 | 60.55.0000 |  | 2026-09-07 | 60.60.0000 |  | 2026-10-05 | 2025-10-24: File Attachments (.png) OSD
CEN/CLC/JTC 13 | DIN | JT013091 | 81344 | prEN XXX | Cybersecurity requirements for products with digital elements – Generic Security Requirements | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-03-05 | 2025-03-05 | 30.99.0979 |  | 2025-12-15 | 40.20.0000 |  | 2026-03-16 | 40.60.0000 |  | 2026-06-08 | 45.99.0979 |  | 2026-09-20 | 50.20.0000 |  | 2026-11-30 | 50.60.0000 |  | 2027-01-25 | 60.55.0000 |  | 2027-02-22 | 60.60.0000 |  | 2027-03-22 | OSD: 2025-02-05
CEN/CLC/JTC 13 | DIN | JT013095 | 82349 | prEN 40000-1-1 | Cybersecurity requirements for products with digital elements - Vocabulary | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2025-07-28 | 2025-07-28 | 30.99.0979 | 2025-10-02 | 2025-10-02 | 40.20.0000 | 2025-10-09 | 2025-10-09 | 40.60.0000 | 2026-01-01 | 2026-01-01 | 45.99.0979 |  | 2026-06-08 | 50.20.0000 |  | 2026-08-17 | 50.60.0000 |  | 2026-10-12 | 60.55.0000 |  | 2026-11-09 | 60.60.0000 |  | 2026-12-07 | 2025-07-18:OSD
CEN/TC 460 | DIN | 00460025 | 81361 |  | Food authenticity — Protocol for the collection of honey reference samples for the construction of authenticity databases | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-02-10 | 2025-02-10 | 30.99.0979 |  | 2025-12-15 | 40.20.0000 |  | 2026-03-16 | 40.60.0000 |  | 2026-06-08 | 45.99.0979 |  | 2026-11-23 | 50.20.0000 |  | 2027-02-01 | 50.60.0000 |  | 2027-03-29 | 60.55.0000 |  | 2027-04-26 | 60.60.0000 |  | 2027-05-24 | 2025-02-04: OSD
CEN/TC 107 | DS | 00107101 | 81261 | prEN 13941-2 rev | District heating pipes - Design and installation of thermal insulated bonded single and twin pipe systems for directly buried hot water networks - Part 2: Installation | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-01-15 | 2025-01-15 | 30.99.0979 |  | 2026-06-10 | 40.20.0000 |  | 2026-09-09 | 40.60.0000 |  | 2026-12-02 | 45.99.0979 |  | 2027-07-28 | 50.20.0000 |  | 2027-10-06 | 50.60.0000 |  | 2027-12-01 | 60.55.0000 |  | 2028-01-03 | 60.60.0000 |  | 2028-01-31 | 2025-01-22:OSD
CEN/TC 261 | AFNOR | 00261546 | 82556 | FprCEN/TS XXXX-1 | Packaging - Design for recycling - Part 1: Process and design criteria to evaluate the recyclability of wood packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-29 | 2025-08-29 | 30.99.0979 |  | 2026-11-01 | [9 empty] | 50.20.0000 |  | 2027-02-01 | 50.60.0000 |  | 2027-04-26 | 60.55.0000 |  | 2027-05-24 | 60.60.0000 |  | 2027-06-21 | 2025-09-24: OSD document
CEN/TC 107 | DS | 00107084 | 73331 | prEN 18213-1 | District heating and district cooling pipes - Bonded single and twin pipe systems for directly buried hot and cold water networks - Part 1: Qualification testing of fitter | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-08-12 | 2024-08-12 | 30.99.0979 | 2025-04-24 | 2025-04-24 | 40.20.0000 | 2025-10-09 | 2025-10-09 | 40.60.0000 | 2026-01-01 | 2026-01-01 | 45.99.0979 |  | 2026-05-25 | 50.20.0000 |  | 2026-08-03 | 50.60.0000 |  | 2026-09-28 | 60.55.0000 |  | 2026-10-26 | 60.60.0000 |  | 2026-11-23
CEN/CLC/JTC 22 | DIN | JT022016 | 82416 | prEN XXX | Color centers — Characterization requirements and test methods | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-01 | 2025-08-01 | 30.99.0979 |  | 2026-03-27 | 40.20.0000 |  | 2026-06-26 | 40.60.0000 |  | 2026-09-18 | 45.99.0979 |  | 2027-05-14 | 50.20.0000 |  | 2027-07-23 | 50.60.0000 |  | 2027-09-17 | 60.55.0000 |  | 2027-10-15 | 60.60.0000 |  | 2027-11-12
CEN/TC 140 | DIN | 00140172 | 83299 |  | In vitro diagnostic examinations — Specifications for pre-examination processes for human specimens for the detection of infectious pathogens — Viruses, bacteria, fungi and parasites | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-01-16 | 2026-01-16 | 30.99.0979 |  | 2028-02-15 | [9 empty] | 50.20.0000 |  | 2028-05-16 | 50.60.0000 |  | 2028-08-08 | 60.55.0000 |  | 2028-09-05 | 60.60.0000 |  | 2028-10-03 | 20260128 - OSD
CEN/TC 256 | DIN | 00256A2A | 75916 | prEN 13749 | Railway applications - Wheelsets and bogies - Running gear structural requirements | Start of draft translation | 40.10.6001 | Homegrown | 10.99.0000 | 2024-06-16 | 2024-06-16 | 30.99.0979 | 2025-12-08 | 2025-12-08 | 40.20.0000 |  | 2026-04-09 | 40.60.0000 |  | 2026-07-03 | 45.99.0979 |  | 2026-12-29 | 50.20.0000 |  | 2027-03-09 | 50.60.0000 |  | 2027-05-04 | 60.55.0000 |  | 2027-06-01 | 60.60.0000 |  | 2027-06-29 | OSD
CEN/TC 88 | DIN | 00088497 | 83062 | prEN 13494 rev | Thermal insulation products for building applications - Determination of the tensile bond strength of the adhesive and of the base coat to the thermal insulation material | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-11-24 | 2025-11-24 | 30.99.0979 |  | 2026-07-20 | 40.20.0000 |  | 2026-10-19 | 40.60.0000 |  | 2027-01-11 | 45.99.0979 |  | 2027-09-06 | 50.20.0000 |  | 2027-11-15 | 50.60.0000 |  | 2028-01-10 | 60.55.0000 |  | 2028-02-07 | 60.60.0000 |  | 2028-03-06 | 2025-12-10: OSD
CEN/CLC/JTC 22 | DIN | JT022021 | 83473 | prCEN/TS XXX | (EAS) Quantum Computing - High-Level Programming Language | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-10 | 2026-02-10 | 30.99.0979 |  | 2026-06-15 | [9 empty] | 50.20.0000 |  | 2026-09-14 | 50.60.0000 |  | 2026-12-07 | 60.55.0000 |  | 2027-01-04 | 60.60.0000 |  | 2027-02-01 | 2026-02-11: This WI is an EAS pilot OSD
CEN/TC 459/SC 9 | AFNOR | EC109095 | 76271 | prEN 10131 rev | Cold rolled uncoated and zinc or zinc-nickel electrolytically coated low carbon and high yield strength steel flat products for cold forming - Tolerances on dimensions and shape | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-19 | 2025-09-19 | 30.99.0979 |  | 2026-05-15 | 40.20.0000 |  | 2026-08-14 | 40.60.0000 |  | 2026-11-06 | 45.99.0979 |  | 2027-07-02 | 50.20.0000 |  | 2027-09-10 | 50.60.0000 |  | 2027-11-05 | 60.55.0000 |  | 2027-12-03 | 60.60.0000 |  | 2028-01-03 | 2025-03-13: OSD
CEN/TC 224 | AFNOR | 00224277 | 77618 | FprCEN/TS 18212-1 | Personal identification - Requirements for biometric products - Part 1: General requirements and application profile definition | Closure of Vote on TS | 50.60.0000 | Homegrown | 10.99.0000 | 2024-11-13 | 2024-11-13 | 30.99.0979 | 2025-04-24 | 2025-04-24 | [9 empty] | 50.20.0000 | 2025-11-27 | 2025-11-27 | 50.60.0000 | 2026-02-19 | 2026-02-19 | 60.55.0000 |  | 2026-03-20 | 60.60.0000 |  | 2026-04-22 | OSD
CEN/TC 440 | DIN | 00440030 | 82175 | FprCEN/TR 17011-2-1 | Electronic Public Procurement - Innovation guideline - Part 2-1: Framework and models of innovative developments in procurement | Acceptance of TR draft | 30.99.0979 | Homegrown | 10.99.0000 | 2025-06-18 | 2025-06-18 | 30.99.0979 | 2026-02-02 | 2026-02-02 | [9 empty] | 50.20.0000 |  | 2026-03-09 | 50.60.0000 |  | 2026-06-01 | 60.55.0000 |  | 2026-06-15 | 60.60.0000 |  | 2026-06-29 | 2025-06-26:OSD
CEN/CLC/JTC 22 | DIN | JT022002 | 79066 | prCEN/CLC/TR XXX | QKD and PQC – An equitable analysis and comparison of both technologies | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-01-17 | 2024-01-17 | 30.99.0979 |  | 2025-01-17 | [9 empty] | 50.20.0000 |  | 2025-02-21 | 50.60.0000 |  | 2025-05-16 | 60.55.0000 |  | 2025-05-30 | 60.60.0000 |  | 2025-06-13 | 2026-01-28 OSD
CEN/TC 260 | DIN | 00260208 | 68254 | prEN 12944-2 | Fertilizers, liming materials and inhibitors - Vocabulary - Part 2: Terms relating to fertilizers | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-10-01 | 2024-10-01 | 30.99.0979 | 2025-10-28 | 2025-10-28 | 40.20.0000 | 2026-01-22 | 2026-01-22 | 40.60.0000 |  | 2026-04-16 | 45.99.0979 |  | 2026-07-15 | 50.20.0000 |  | 2026-09-23 | 50.60.0000 |  | 2026-11-18 | 60.55.0000 |  | 2026-12-16 | 60.60.0000 |  | 2027-01-13 | 2025-07-23:OSD
CEN/TC 152 | UNI | 00152022 | 80209 | prEN 13782 | Temporary structure - Tents - Safety | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-06-17 | 2024-06-17 | 30.99.0979 | 2025-07-24 | 2025-07-24 | 40.20.0000 | 2025-11-13 | 2025-11-13 | 40.60.0000 | 2026-02-05 | 2026-02-05 | 45.99.0979 |  | 2026-12-30 | 50.20.0000 |  | 2027-03-10 | 50.60.0000 |  | 2027-05-05 | 60.55.0000 |  | 2027-06-02 | 60.60.0000 |  | 2027-06-30 | 2025-01-17: OSD
CEN/CLC/JTC 13 | DIN | JT013089 | 81335 | prEN 40000-1-2 | Cybersecurity requirements for products with digital elements - Part 1-2: Principles for cyber resilience | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2025-03-05 | 2025-03-05 | 30.99.0979 | 2025-09-29 | 2025-09-29 | 40.20.0000 | 2025-10-09 | 2025-10-09 | 40.60.0000 | 2026-01-01 | 2026-01-01 | 45.99.0979 |  | 2026-08-27 | 50.20.0000 |  | 2026-11-05 | 50.60.0000 |  | 2027-01-04 | 60.55.0000 |  | 2027-02-01 | 60.60.0000 |  | 2027-03-01 | 2025-02-05 : OSD
CEN/TC 107 | DS | 00107097 | 81113 | prEN 489-2 | District heating pipes - Factory made flexible pipe systems - Joint casing systems | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-12-12 | 2024-12-12 | 30.99.0979 | 2025-07-16 | 2025-07-16 | 40.20.0000 | 2025-11-06 | 2025-11-06 | 40.60.0000 | 2026-01-29 | 2026-01-29 | 45.99.0979 |  | 2026-09-24 | 50.20.0000 |  | 2026-12-03 | 50.60.0000 |  | 2027-01-28 | 60.55.0000 |  | 2027-02-25 | 60.60.0000 |  | 2027-03-25 | 2024-12-19 : OSD
CEN/CLC/JTC 22 | DIN | JT022013 | 82410 | prEN XXX | Entangled Photon-Pair Sources — Characterization requirements and test methods | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-01 | 2025-08-01 | 30.99.0979 |  | 2026-03-27 | 40.20.0000 |  | 2026-06-26 | 40.60.0000 |  | 2026-09-18 | 45.99.0979 |  | 2027-05-14 | 50.20.0000 |  | 2027-07-23 | 50.60.0000 |  | 2027-09-17 | 60.55.0000 |  | 2027-10-15 | 60.60.0000 |  | 2027-11-12 | 2025-08-05: OSD
CEN/TC 207 | UNI | 00207321 | 80526 |  | Furniture — Circularity — Evaluation method for maintenance, repair and refurbishing capability | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-26 | 2025-09-26 | 30.99.0979 |  | 2026-05-22 | 40.20.0000 |  | 2026-08-21 | 40.60.0000 |  | 2026-11-13 | 45.99.0979 |  | 2027-07-09 | 50.20.0000 |  | 2027-09-17 | 50.60.0000 |  | 2027-11-12 | 60.55.0000 |  | 2027-12-10 | 60.60.0000 |  | 2028-01-07 | OSD
CEN/TC 107 | DS | 00107102 | 81277 | prEN 13941-1 rev | District heating pipes - Design and installation of thermal insulated bonded single and twin pipe systems for directly buried hot water networks - Part 1: Design | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-01-16 | 2025-01-16 | 30.99.0979 |  | 2026-06-11 | 40.20.0000 |  | 2026-09-10 | 40.60.0000 |  | 2026-12-03 | 45.99.0979 |  | 2027-07-29 | 50.20.0000 |  | 2027-10-07 | 50.60.0000 |  | 2027-12-02 | 60.55.0000 |  | 2028-01-03 | 60.60.0000 |  | 2028-01-31 | 2025-01-22:OSD
CEN/TC 138 | AFNOR | 00138325 | 83414 |  | Non-destructive testing – Evaluation of testing data – Guideline to estimate the reliability of applications | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-03 | 2026-02-03 | 30.99.0979 |  | 2026-11-30 | 40.20.0000 |  | 2027-03-01 | 40.60.0000 |  | 2027-05-24 | 45.99.0979 |  | 2027-11-16 | 50.20.0000 |  | 2028-01-25 | 50.60.0000 |  | 2028-03-21 | 60.55.0000 |  | 2028-04-18 | 60.60.0000 |  | 2028-05-16 | OSD
CEN/TC 275 | DIN | 00275385 | 80389 |  | Foodstuffs - Determination of elements and their chemical species - Determination of methylmercury in foodstuffs by HPLC-ICP-MS | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-14 | 2025-08-14 | 30.99.0979 |  | 2026-10-22 | 40.20.0000 |  | 2027-01-21 | 40.60.0000 |  | 2027-04-15 | 45.99.0979 |  | 2027-05-27 | 50.20.0000 |  | 2027-08-05 | 50.60.0000 |  | 2027-09-30 | 60.55.0000 |  | 2027-10-28 | 60.60.0000 |  | 2027-11-25 | OSD
CEN/TC 261 | AFNOR | 00261548 | 82673 |  | CEN/TS XXXX, Packaging — Design for recycling — Part 1: Process and design criteria to evaluate the recyclability of textile packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-19 | 2025-09-19 | 30.99.0979 |  | 2025-12-28 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 2025-09-24:OSD
CEN/TC 245 | AFNOR | 00245055 | 79212 | prEN 1648-1 rev | Leisure accommodation vehicles – Nominal 12 V/24 V/48 V direct current extra low voltage electrical installations - Part 1: Caravans | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-05 | 2026-02-05 | 30.99.0979 |  | 2026-10-01 | 40.20.0000 |  | 2027-01-04 | 40.60.0000 |  | 2027-03-29 | 45.99.0979 |  | 2027-11-18 | 50.20.0000 |  | 2028-01-27 | 50.60.0000 |  | 2028-03-23 | 60.55.0000 |  | 2028-04-20 | 60.60.0000 |  | 2028-05-18 | OSD
CEN/TC 332 | DIN | 00332113 | 82837 | prEN 15154-6 rev | Emergency safety showers - Part 6: Plumbed-in multiple nozzle body showers for sites other than laboratories | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-07 | 2025-10-07 | 30.99.0979 |  | 2026-06-02 | 40.20.0000 |  | 2026-09-01 | 40.60.0000 |  | 2026-11-24 | 45.99.0979 |  | 2027-07-20 | 50.20.0000 |  | 2027-09-28 | 50.60.0000 |  | 2027-11-23 | 60.55.0000 |  | 2027-12-21 | 60.60.0000 |  | 2028-01-18 | 2025-10-13: OSD
CEN/TC 169 | DIN | 00169098 | 76697 | prEN 17037 rev | Daylight in buildings | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-19 | 2025-09-19 | 30.99.0979 |  | 2026-11-27 | 40.20.0000 |  | 2027-02-26 | 40.60.0000 |  | 2027-05-21 | 45.99.0979 |  | 2027-07-02 | 50.20.0000 |  | 2027-09-10 | 50.60.0000 |  | 2027-11-05 | 60.55.0000 |  | 2027-12-03 | 60.60.0000 |  | 2028-01-03 | 2025-02-13: OSD
CEN/TC 162 | DIN | 00162510 | 81659 | prEN 469 rev | Protective clothing for firefighters - Performance requirements for protective clothing for firefighting activities | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-03-27 | 2025-03-27 | 30.99.0979 |  | 2025-10-28 | 40.20.0000 |  | 2026-01-27 | 40.60.0000 |  | 2026-04-21 | 45.99.0979 |  | 2027-01-07 | 50.20.0000 |  | 2027-03-18 | 50.60.0000 |  | 2027-05-13 | 60.55.0000 |  | 2027-06-10 | 60.60.0000 |  | 2027-07-08 | 2025-04-02: OSD
CEN/TC 182 | DIN | 00182095 | 73150 | prEN 378-1 | Refrigerating systems and heat pumps - Safety and environmental requirements - Part 1: Basic requirements, definitions, classification and selection criteria | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2023-10-27 | 2023-10-27 | 30.99.0979 | 2025-01-31 | 2025-01-31 15:45 | 40.20.0000 | 2025-07-03 | 2025-07-03 | 40.60.0000 | 2025-09-25 | 2025-09-25 | 45.99.0979 |  | 2026-05-08 | 50.20.0000 |  | 2026-07-17 | 50.60.0000 |  | 2026-09-11 | 60.55.0000 |  | 2026-10-09 | 60.60.0000 |  | 2026-11-06 | OSD
CEN/TC 473 | SIS | 00473004 | 81269 | prEN XXX | Circular Economy - Extended Producer Responsibility (EPR) - Requirements and guidelines for Producer Responsibility Organizations (PRO) | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-06-05 | 2025-06-05 | 30.99.0979 |  | 2026-10-29 | 40.20.0000 |  | 2027-01-28 | 40.60.0000 |  | 2027-04-22 | 45.99.0979 |  | 2027-12-18 | 50.20.0000 |  | 2028-02-28 | 50.60.0000 |  | 2028-04-24 | 60.55.0000 |  | 2028-05-22 | 60.60.0000 |  | 2028-06-19 | 2025-10-29: OSD until prior to submission to ENQ, project will be converted into VA// CEN lead and transfered to ISO OSD.
CEN/TC 261 | AFNOR | 00261536 | 81848 |  | Packaging — Design for recycling — Part 1: Process and design criteria to evaluate the recyclability of steel packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 2025-04-28:OSD
CEN/TC 245 | AFNOR | 00245056 | 79213 | prEN 1648-2 rev | Leisure accommodation vehicles — Nominal 12 V/ 24 V/ 48 V direct current extra low voltage electrical installations — Part 2: Motor caravans | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-05 | 2026-02-05 | 30.99.0979 |  | 2026-10-01 | 40.20.0000 |  | 2027-01-04 | 40.60.0000 |  | 2027-03-29 | 45.99.0979 |  | 2027-11-18 | 50.20.0000 |  | 2028-01-27 | 50.60.0000 |  | 2028-03-23 | 60.55.0000 |  | 2028-04-20 | 60.60.0000 |  | 2028-05-18 | OSD
CEN/TC 275 | DIN | 00275393 | 83412 | prEN 16852 rev | Foodstuffs - Determination of ethyl carbamate in stone fruit spirits, fruit marc spirits and other spirit drinks - GC-MS method | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-03 | 2026-02-03 | 30.99.0979 |  | 2026-04-22 | 40.20.0000 |  | 2026-07-22 | 40.60.0000 |  | 2026-10-14 | 45.99.0979 |  | 2027-11-16 | 50.20.0000 |  | 2028-01-25 | 50.60.0000 |  | 2028-03-21 | 60.55.0000 |  | 2028-04-18 | 60.60.0000 |  | 2028-05-16 | OSD
CEN/TC 473 | SIS | 00473005 | 81513 |  | Circular economy – Quality classification for remanufacturing processes | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-03-04 | 2025-03-04 | 30.99.0979 |  | 2026-07-28 | 40.20.0000 |  | 2026-10-27 | 40.60.0000 |  | 2027-01-19 | 45.99.0979 |  | 2027-09-15 | 50.20.0000 |  | 2027-11-24 | 50.60.0000 |  | 2028-01-19 | 60.55.0000 |  | 2028-02-16 | 60.60.0000 |  | 2028-03-15 | 2025-03-27: OSD
CEN/CLC/JTC 21 | DS | JT021008 | 76986 | prEN 18229-1 | AI trustworthiness framework – Part 1: Logging, transparency and human oversight | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-03-20 | 2024-03-20 | 30.99.0979 |  | 2025-08-31 | 40.20.0000 |  | 2025-12-01 | 40.60.0000 |  | 2026-02-23 | 45.99.0979 |  | 2026-11-30 | 50.20.0000 |  | 2027-02-08 | 50.60.0000 |  | 2027-04-05 | 60.55.0000 |  | 2027-05-03 | 60.60.0000 |  | 2027-05-31 | OSD
CEN/TC 440 | DIN | 00440025 | 79786 | prEN 17014-2 | Electronic public procurement - Pre-award - Part 2: Transactions | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-04-01 | 2024-04-01 | 30.99.0979 | 2025-10-17 | 2025-10-17 | 40.20.0000 | 2026-01-29 | 2026-01-29 | 40.60.0000 |  | 2026-04-23 | 45.99.0979 |  | 2026-10-12 | 50.20.0000 |  | 2026-12-21 | 50.60.0000 |  | 2027-02-15 | 60.55.0000 |  | 2027-03-15 | 60.60.0000 |  | 2027-04-12 | OSD
CEN/TC 275 | DIN | 00275389 | 81469 | prEN 15634-7 | Foodstuffs - Detection of food allergens by molecular biological methods - Part 7: Peanut (Arachis hypogaea) - Qualitative detection of a specific DNA sequence in food by real-time PCR | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2025-02-20 | 2025-02-20 | 30.99.0979 | 2025-10-17 | 2025-10-17 | 40.20.0000 | 2026-01-22 | 2026-01-22 | 40.60.0000 |  | 2026-04-16 | 45.99.0979 |  | 2026-12-03 | 50.20.0000 |  | 2027-02-11 | 50.60.0000 |  | 2027-04-08 | 60.55.0000 |  | 2027-05-06 | 60.60.0000 |  | 2027-06-03 | 2025-03-04: OSD
CEN/TC 182 | DIN | 00182101 | 77731 | prEN 14624 | Performance of portable locating leak detectors and of fixed gas detectors for all refrigerants | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-08-09 | 2024-08-09 | 30.99.0979 | 2025-07-08 | 2025-07-08 | 40.20.0000 | 2025-11-06 | 2025-11-06 | 40.60.0000 | 2026-01-29 | 2026-01-29 | 45.99.0979 |  | 2026-05-22 | 50.20.0000 |  | 2026-07-31 | 50.60.0000 |  | 2026-09-25 | 60.55.0000 |  | 2026-10-23 | 60.60.0000 |  | 2026-11-20 | OSD
CEN/TC 207 | UNI | 00207328 | 81825 |  | Children’s furniture – Tables – Safety requirements and test methods | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-11 | 2025-04-11 | 30.99.0979 |  | 2025-12-05 | 40.20.0000 |  | 2026-03-06 | 40.60.0000 |  | 2026-05-29 | 45.99.0979 |  | 2027-01-22 | 50.20.0000 |  | 2027-04-02 | 50.60.0000 |  | 2027-05-28 | 60.55.0000 |  | 2027-06-25 | 60.60.0000 |  | 2027-07-23 | 2025-04-30:OSD
CEN/TC 350 | AFNOR | 00350039 | 75207 | prEN 18177 | Circular economy in the construction sector - Framework, principles, and definitions | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-05-02 | 2024-05-02 | 30.99.0979 | 2025-01-16 | 2025-01-16 09:11 | 40.20.0000 | 2025-04-10 | 2025-04-10 | 40.60.0000 | 2025-07-03 | 2025-07-03 | 45.99.0979 |  | 2026-02-12 | 50.20.0000 |  | 2026-04-23 | 50.60.0000 |  | 2026-06-18 | 60.55.0000 |  | 2026-07-16 | 60.60.0000 |  | 2026-08-13 | OSD
CEN/TC 261 | AFNOR | 00261532 | 81843 |  | Packaging — Design for recycling — Part 2: Evaluation processes for the sortability of packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 202/04/28:OSD
CEN/TC 460 | DIN | 00460031 | 82984 |  | Food authenticity — Quantification of adulterant plant material in paprika/chilli, saffron, cumin, turmeric, oregano and black pepper by quantitative PCR | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-11-10 | 2025-11-10 | 30.99.0979 |  | 2027-01-01 | [9 empty] | 50.20.0000 |  | 2027-04-02 | 50.60.0000 |  | 2027-06-25 | 60.55.0000 |  | 2027-07-23 | 60.60.0000 |  | 2027-08-20 | 2025-11-24: OSD
CEN/CLC/JTC 13 | DIN | JT013090 | 81343 | prEN 40000-1-3 | Cybersecurity requirements for products with digital elements - Part 1-3: Vulnerability Handling | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2025-03-05 | 2025-03-05 | 30.99.0979 | 2025-11-27 | 2025-11-27 | 40.20.0000 | 2025-12-11 | 2025-12-11 | 40.60.0000 |  | 2026-03-05 | 45.99.0979 |  | 2025-06-06 | 50.20.0000 |  | 2025-08-18 | 50.60.0000 |  | 2025-10-13 | 60.55.0000 |  | 2025-11-10 | 60.60.0000 |  | 2025-12-08 | 2025-02-05 : OSD
CEN/TC 19 | NEN | 00019690 | 83463 | prEN 16568 rev | Automotive fuels - Blends of Fatty acid methyl ester (FAME) with diesel fuel - Determination of oxidation stability by rapidly accelerated oxidation method at 120 °C | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-10 | 2026-02-10 | 30.99.0979 |  | 2026-10-06 | 40.20.0000 |  | 2027-01-05 | 40.60.0000 |  | 2027-03-30 | 45.99.0979 |  | 2027-11-23 | 50.20.0000 |  | 2028-02-01 | 50.60.0000 |  | 2028-03-28 | 60.55.0000 |  | 2028-04-25 | 60.60.0000 |  | 2028-05-23 | OSD
CEN/TC 473 | SIS | 00473002 | 80617 | prCEN/TS 18333 | Circular Economy - Practical information and guidance for the implementation of ISO 59004:2024 in Europe | Acceptance of TS draft | 30.99.0979 | Homegrown | 10.99.0000 | 2024-09-10 | 2024-09-10 | 30.99.0979 | 2025-12-24 | 2025-12-24 | [9 empty] | 50.20.0000 |  | 2026-03-12 | 50.60.0000 |  | 2026-06-04 | 60.55.0000 |  | 2026-07-02 | 60.60.0000 |  | 2026-07-30 | OSD
CEN/CLC/JTC 22 | DIN | JT022022 | 83479 | prCEN/TS XXX | (EAS) Roadmap for Post-Processing Software in Space | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-10 | 2026-02-10 | 30.99.0979 |  | 2026-06-15 | [9 empty] | 50.20.0000 |  | 2026-09-14 | 50.60.0000 |  | 2026-12-07 | 60.55.0000 |  | 2027-01-04 | 60.60.0000 |  | 2027-02-01 | 2026-02-11: This WI is an EAS pilot OSD
CEN/TC 371 | NEN | 00371015 | 83171 |  | Energy performance requirements – Operational rating – Framework for assess | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-01-15 | 2026-01-15 | 30.99.0979 |  | 2026-09-10 | 40.20.0000 |  | 2026-12-10 | 40.60.0000 |  | 2027-03-04 | 45.99.0979 |  | 2027-10-28 | 50.20.0000 |  | 2028-01-06 | 50.60.0000 |  | 2028-03-02 | 60.55.0000 |  | 2028-03-30 | 60.60.0000 |  | 2028-04-27 | 2025-12-23: OSD
CEN/TC 224 | AFNOR | 00224287 | 81429 |  | Decomposition of the EUDI Wallet – Part 1: Decomposition of the Solution by Module in the objective of Functional and Security Certifications | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-02-13 | 2025-02-13 | 30.99.0979 |  | 2026-11-02 | [9 empty] | 50.20.0000 |  | 2027-02-01 | 50.60.0000 |  | 2027-04-26 | 60.55.0000 |  | 2027-05-24 | 60.60.0000 |  | 2027-06-21 | 2025-02-18: OSD
CEN/TC 224 | AFNOR | 00224282 | 79593 | FprCEN/TS 18297 | EUDI Wallet Held Assets Access Control, Operation and Management | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-08 | 2025-10-08 | 30.99.0979 |  | 2026-10-02 | [9 empty] | 50.20.0000 |  | 2027-01-04 | 50.60.0000 |  | 2027-03-29 | 60.55.0000 |  | 2027-04-26 | 60.60.0000 |  | 2027-05-24 | OSD
CEN/TC 147 | SFS | 00147191 | 77315 | prEN 13852-2 rev | Cranes - Offshore cranes - Part 2: Floating cranes | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-01-07 | 2026-01-07 | 30.99.0979 |  | 2026-09-02 | 40.20.0000 |  | 2026-12-02 | 40.60.0000 |  | 2027-02-24 | 45.99.0979 |  | 2027-10-20 | 50.20.0000 |  | 2028-01-03 | 50.60.0000 |  | 2028-02-28 | 60.55.0000 |  | 2028-03-27 | 60.60.0000 |  | 2028-04-24 | 2024-12-19 : OSD
CEN/TC 263 | BSI | 00263048 | 82875 |  | Test requirements for fire-protection storage cabinets for lithium-ion batteries in the case of thermal runaway | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-15 | 2025-10-15 | 30.99.0979 |  | 2026-06-10 | 40.20.0000 |  | 2026-09-09 | 40.60.0000 |  | 2026-12-02 | 45.99.0979 |  | 2027-07-28 | 50.20.0000 |  | 2027-10-06 | 50.60.0000 |  | 2027-12-01 | 60.55.0000 |  | 2028-01-03 | 60.60.0000 |  | 2028-01-31 | 2025-11-13: OSD
CEN/TC 88 | DIN | 00088499 | 83065 | prEN 13497 rev | Thermal insulation products for building applications - Determination of the resistance to impact of external thermal insulation composite systems (ETICS) | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-11-25 | 2025-11-25 | 30.99.0979 |  | 2026-07-21 | 40.20.0000 |  | 2026-10-20 | 40.60.0000 |  | 2027-01-12 | 45.99.0979 |  | 2027-09-07 | 50.20.0000 |  | 2027-11-16 | 50.60.0000 |  | 2028-01-11 | 60.55.0000 |  | 2028-02-08 | 60.60.0000 |  | 2028-03-07
CEN/TC 243 | BSI | 00243046 | 82918 | prEN 17141 rev | Cleanrooms and associated controlled environments - Microbiological contamination control | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-27 | 2025-10-27 | 30.99.0979 |  | 2026-06-22 | 40.20.0000 |  | 2026-09-21 | 40.60.0000 |  | 2026-12-14 | 45.99.0979 |  | 2027-08-09 | 50.20.0000 |  | 2027-10-18 | 50.60.0000 |  | 2027-12-13 | 60.55.0000 |  | 2028-01-10 | 60.60.0000 |  | 2028-02-07 | 2025-11-13: OSD
CEN/TC 440 | DIN | 00440032 | 83403 |  | Electronic Public Procurement - Ordering - Part 3-1: Syntax Binding, UBL | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-01-30 | 2026-01-30 | 30.99.0979 |  | 2027-02-09 | [9 empty] | 50.20.0000 |  | 2027-05-11 | 50.60.0000 |  | 2027-08-03 | 60.55.0000 |  | 2027-08-31 | 60.60.0000 |  | 2027-09-28 | (2026-02-03-OSD)
CEN/TC 440 | DIN | 00440028 | 80289 | prEN 17011-5 | Electronic Public Procurement - Architecture - Part 5: Semantic architecture | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-07-03 | 2024-07-03 | 30.99.0979 |  | 2025-11-01 | [9 empty] | 50.20.0000 |  | 2026-02-02 | 50.60.0000 |  | 2026-04-27 | 60.55.0000 |  | 2026-05-26 | 60.60.0000 |  | 2026-06-23 | OSD
CEN/TC 261 | AFNOR | 00261540 | 81852 |  | Packaging — Design for recycling — Part 2: Testing protocol for aluminium packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 202/04/28:OSD
CEN/TC 254 | NEN | 00254200 | 82966 | prEN 13948 rev | Flexible sheets for waterproofing - Bitumen, plastic and rubber sheets for roof waterproofing - Determination of resistance to root penetration | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-11-04 | 2025-11-04 | 30.99.0979 |  | 2026-06-30 | 40.20.0000 |  | 2026-09-29 | 40.60.0000 |  | 2026-12-22 | 45.99.0979 |  | 2027-08-17 | 50.20.0000 |  | 2027-10-26 | 50.60.0000 |  | 2027-12-21 | 60.55.0000 |  | 2028-01-18 | 60.60.0000 |  | 2028-02-15 | 2025-11-13: OSD
CEN/TC 182 | DIN | 00182094 | 73149 | prEN 378-5 | Refrigerating systems and heat pumps - Safety and environmental requirements - Part 5: Safety classification and information about refrigerants | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2023-10-27 | 2023-10-27 | 30.99.0979 | 2025-01-31 | 2025-01-31 15:48 | 40.20.0000 | 2025-07-03 | 2025-07-03 | 40.60.0000 | 2025-09-25 | 2025-09-25 | 45.99.0979 |  | 2026-05-08 | 50.20.0000 |  | 2026-07-17 | 50.60.0000 |  | 2026-09-11 | 60.55.0000 |  | 2026-10-09 | 60.60.0000 |  | 2026-11-06 | OSD
CEN/CLC/JTC 22 | DIN | JT022023 | 83480 | prCEN/TS XXX-1 | (EAS) Quantum Computing - Hardware Abstraction Layer - Part 1: Descriptions and functional requirements | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-10 | 2026-02-10 | 30.99.0979 |  | 2026-06-15 | [9 empty] | 50.20.0000 |  | 2026-09-14 | 50.60.0000 |  | 2026-12-07 | 60.55.0000 |  | 2027-01-04 | 60.60.0000 |  | 2027-02-01 | 2026-02-11: This WI is an EAS pilot OSD
CEN/TC 19 | NEN | 00019689 | 83295 | prCEN/TR 18172 rev | Determination of aerobic biological degradation of fully formulated lubricants in an aqueous solution - Test method based on CO2-production of Lubricants - Study report | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-01-15 | 2026-01-15 | 30.99.0979 |  | 2027-01-15 | [9 empty] | 50.20.0000 |  | 2027-02-19 | 50.60.0000 |  | 2027-05-14 | 60.55.0000 |  | 2027-05-28 | 60.60.0000 |  | 2027-06-11 | OSD
CEN/CLC/JTC 21 | DS | JT021036 | 80353 | prEN 18283 | Artificial Intelligence - Concepts, measures and requirements for managing bias in AI systems | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-08-21 | 2024-08-21 | 30.99.0979 |  | 2026-01-16 | 40.20.0000 |  | 2026-04-17 | 40.60.0000 |  | 2026-07-10 | 45.99.0979 |  | 2027-03-03 | 50.20.0000 |  | 2027-05-12 | 50.60.0000 |  | 2027-07-07 | 60.55.0000 |  | 2027-08-04 | 60.60.0000 |  | 2027-09-01 | OSD
CEN/TC 224 | AFNOR | 00224280 | 77621 | FprCEN/TS 18212-5 | Personal identification - Requirements for biometric products - Part 5: Face biometrics | Submission to Vote on TS | 50.20.0000 | Homegrown | 10.99.0000 | 2024-11-13 | 2024-11-13 | 30.99.0979 | 2025-12-08 | 2025-12-08 | [9 empty] | 50.20.0000 | 2026-01-29 | 2026-01-29 | 50.60.0000 |  | 2026-04-23 | 60.55.0000 |  | 2026-05-21 | 60.60.0000 |  | 2026-06-18 | OSD
CEN/TC 155 | NEN | 00155A2R | 83216 | prCEN/TS 1046 rev | Thermoplastics piping and ducting systems - Outside the building structures for gravity and pressurised systems - Trench installation | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-12-29 | 2025-12-29 | 30.99.0979 |  | 2027-01-01 | [9 empty] | 50.20.0000 |  | 2027-04-02 | 50.60.0000 |  | 2027-06-25 | 60.55.0000 |  | 2027-07-23 | 60.60.0000 |  | 2027-08-20 | 2026-01-05: OSD
CEN/TC 19 | NEN | 00019688 | 82877 | prEN 16423 rev | Liquefied petroleum gases - Determination of dissolved residue - Gas chromatographic method using liquid, on-column injection | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-16 | 2025-10-16 | 30.99.0979 |  | 2026-06-11 | 40.20.0000 |  | 2026-09-10 | 40.60.0000 |  | 2026-12-03 | 45.99.0979 |  | 2027-07-29 | 50.20.0000 |  | 2027-10-07 | 50.60.0000 |  | 2027-12-02 | 60.55.0000 |  | 2028-01-03 | 60.60.0000 |  | 2028-01-31 | 2025-11-13: OSD
CEN/TC 354 | AFNOR | 00354010 | 80375 | prEN 16230-1 rev | Leisure karts - Part 1: Safety requirements and test methods for karts | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2023-12-20 | 2023-12-20 | 30.99.0979 |  | 2026-08-02 | 40.20.0000 |  | 2026-11-02 | 40.60.0000 |  | 2027-01-25 | 45.99.0979 |  | 2027-03-02 | 50.20.0000 |  | 2027-05-11 | 50.60.0000 |  | 2027-07-06 | 60.55.0000 |  | 2027-08-03 | 60.60.0000 |  | 2027-08-31 | OSD
CEN/TC 261 | AFNOR | 00261537 | 81849 |  | Packaging — Design for recycling — Part 2: Testing protocol for steel packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 2025-04-28:OSD
CEN/TC 261 | AFNOR | 00261531 | 81842 |  | Packaging — Design for recycling — Part 2: Testing protocol for paper and cardboard packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 202/04/28:OSD
CEN/CLC/JTC 21 | DS | JT021035 | 80227 | prEN 18287 | Sustainable Artificial Intelligence – Guidelines and metrics for the environmental impact of artificial intelligence systems and services | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-30 | 2025-09-30 | 30.99.0979 |  | 2026-05-26 | 40.20.0000 |  | 2026-08-25 | 40.60.0000 |  | 2026-11-17 | 45.99.0979 |  | 2027-07-13 | 50.20.0000 |  | 2027-09-21 | 50.60.0000 |  | 2027-11-16 | 60.55.0000 |  | 2027-12-14 | 60.60.0000 |  | 2028-01-11 | 2025/09/25: OSD
CEN/CLC/JTC 22 | DIN | JT022010 | 81991 | prEN XXX | RF & DC lines cabling components for quantum technologies down to ultra-low temperature – Key parameters and test methods | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-16 | 2025-04-16 | 30.99.0979 |  | 2025-12-10 | 40.20.0000 |  | 2026-03-11 | 40.60.0000 |  | 2026-06-03 | 45.99.0979 |  | 2027-01-27 | 50.20.0000 |  | 2027-04-07 | 50.60.0000 |  | 2027-06-02 | 60.55.0000 |  | 2027-06-30 | 60.60.0000 |  | 2027-07-28 | 2025-05-20:OSD
CEN/TC 256 | DIN | 00256A1Q | 74943 | prCEN/TR 14363-6 | Railway applications - Testing and simulation for the assessment of running characteristics of railway vehicles operated on the heavy rail network - Part 6: Technical Report providing background information to the EN 14363 series of standards | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-09-13 | 2024-09-13 | 30.99.0979 |  | 2026-06-14 | [9 empty] | 50.20.0000 |  | 2026-07-20 | 50.60.0000 |  | 2026-10-12 | 60.55.0000 |  | 2026-10-26 | 60.60.0000 |  | 2026-11-09 | 2025-03-17: OSD
CEN/CLC/JTC 21 | DS | JT021044 | 80792 | prEN 18288 | Artificial Intelligence - Taxonomy of AI tasks in computer vision | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-11-20 | 2024-11-20 | 30.99.0979 |  | 2026-10-28 | 40.20.0000 |  | 2027-01-27 | 40.60.0000 |  | 2027-04-21 | 45.99.0979 |  | 2027-06-02 | 50.20.0000 |  | 2027-08-11 | 50.60.0000 |  | 2027-10-06 | 60.55.0000 |  | 2027-11-03 | 60.60.0000 |  | 2027-12-01 | OSD
CEN/TC 440 | DIN | 00440031 | 82176 | FprCEN/TR 17011-2-2 | Electronic Public Procurement - Innovation guideline - Part 2-2: Identification of standardization activities to support innovative developments in procurement | Acceptance of TR draft | 30.99.0979 | Homegrown | 10.99.0000 | 2025-06-18 | 2025-06-18 | 30.99.0979 | 2026-02-02 | 2026-02-02 | [9 empty] | 50.20.0000 |  | 2026-03-09 | 50.60.0000 |  | 2026-06-01 | 60.55.0000 |  | 2026-06-15 | 60.60.0000 |  | 2026-06-29 | 2025-06-26:OSD
CEN/TC 440 | DIN | 00440024 | 79785 | prEN 17014-1 | Electronic public procurement - Pre-award - Part 1: Choreographies | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-04-01 | 2024-04-01 | 30.99.0979 | 2025-10-17 | 2025-10-17 | 40.20.0000 | 2026-01-29 | 2026-01-29 | 40.60.0000 |  | 2026-04-23 | 45.99.0979 |  | 2026-10-12 | 50.20.0000 |  | 2026-12-21 | 50.60.0000 |  | 2027-02-15 | 60.55.0000 |  | 2027-03-15 | 60.60.0000 |  | 2027-04-12 | OSD
CEN/TC 275 | DIN | 00275391 | 81471 | prEN 15634-9 | Foodstuffs - Detection of food allergens by molecular biological methods - Part 9: Fish - Qualitative detection of a specific DNA sequence in food by real-time PCR | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2025-02-20 | 2025-02-20 | 30.99.0979 | 2025-10-17 | 2025-10-17 | 40.20.0000 | 2026-01-22 | 2026-01-22 | 40.60.0000 |  | 2026-04-16 | 45.99.0979 |  | 2026-12-03 | 50.20.0000 |  | 2027-02-11 | 50.60.0000 |  | 2027-04-08 | 60.55.0000 |  | 2027-05-06 | 60.60.0000 |  | 2027-06-03 | 2025-03-04: OSD
CEN/TC 440 | DIN | 00440029 | 82174 | FprCEN/TR 17011-2-3 | Electronic Public Procurement - Innovation guideline - Part 2-3: Legislation and regulations to enable and support innovative developments in procurement | Acceptance of TR draft | 30.99.0979 | Homegrown | 10.99.0000 | 2025-06-18 | 2025-06-18 | 30.99.0979 | 2026-02-02 | 2026-02-02 | [9 empty] | 50.20.0000 |  | 2026-03-09 | 50.60.0000 |  | 2026-06-01 | 60.55.0000 |  | 2026-06-15 | 60.60.0000 |  | 2026-06-29 | 2025-06-26:OSD
CEN/TC 440 | DIN | 00440026 | 79792 | prCEN/TS XXX | Electronic Public Procurement - Pre-Award - Part 3-1: Syntax Binding, UBL | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-03-25 | 2024-03-25 | 30.99.0979 |  | 2026-01-01 | [9 empty] | 50.20.0000 |  | 2026-04-02 | 50.60.0000 |  | 2026-06-25 | 60.55.0000 |  | 2026-07-23 | 60.60.0000 |  | 2026-08-20 | OSD
CEN/TC 194 | AFNOR | 00194170 | 80131 |  | Evaluation of the suitability of metal and alloy articles in contact with foodstuffs during microwave heating | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-01-22 | 2025-01-22 | 30.99.0979 |  | 2025-09-17 | 40.20.0000 |  | 2025-12-17 | 40.60.0000 |  | 2026-03-11 | 45.99.0979 |  | 2026-11-04 | 50.20.0000 |  | 2027-01-13 | 50.60.0000 |  | 2027-03-10 | 60.55.0000 |  | 2027-04-07 | 60.60.0000 |  | 2027-05-05 | 2025-02-05: OSD
CEN/CLC/JTC 25 | UNI | JT025015 | 83518 | prCEN/TS XXX | Requirements for Implementation tools and artefacts for data governance, data management and data quality supporting trusted data sharing | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-18 | 2026-02-18 | 30.99.0979 |  | 2026-06-15 | [9 empty] | 50.20.0000 |  | 2026-09-14 | 50.60.0000 |  | 2026-12-07 | 60.55.0000 |  | 2027-01-04 | 60.60.0000 |  | 2027-02-01 | 2026-02-20: This WI is an EAS pilot OSD
CEN/TC 275 | DIN | 00275388 | 81468 | prEN 15634-6 | Foodstuffs - Detection of food allergens by molecular biological methods - Part 6: Wheat (Triticum L.) and Rye (Secale cereale) - Qualitative detection of a specific DNA sequence in cooked sausages by real-time PCR | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2025-02-20 | 2025-02-20 | 30.99.0979 | 2025-10-17 | 2025-10-17 | 40.20.0000 | 2026-01-22 | 2026-01-22 | 40.60.0000 |  | 2026-04-16 | 45.99.0979 |  | 2026-12-03 | 50.20.0000 |  | 2027-02-11 | 50.60.0000 |  | 2027-04-08 | 60.55.0000 |  | 2027-05-06 | 60.60.0000 |  | 2027-06-03 | 2025-03-04: OSD
CEN/TC 408 | AFNOR | 00408027 | 83413 |  | Biomethane and other renewable and low-carbon methane rich gases – Specifications for injection in the natural gas network and for mixtures with natural gas as automotive fuel | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-03 | 2026-02-03 | 30.99.0979 |  | 2026-09-29 | 40.20.0000 |  | 2027-01-04 | 40.60.0000 |  | 2027-03-29 | 45.99.0979 |  | 2027-11-16 | 50.20.0000 |  | 2028-01-25 | 50.60.0000 |  | 2028-03-21 | 60.55.0000 |  | 2028-04-18 | 60.60.0000 |  | 2028-05-16 | OSD
CEN/TC 107 | DS | 00107086 | 73333 | prEN 18213-2 | District heating and district cooling pipes - Bonded single and twin pipe systems for directly buried hot and cold water networks - Part 2: Qualification testing of PE-Welder | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-08-12 | 2024-08-12 | 30.99.0979 | 2025-04-24 | 2025-04-24 | 40.20.0000 | 2025-10-09 | 2025-10-09 | 40.60.0000 | 2026-01-01 | 2026-01-01 | 45.99.0979 |  | 2026-05-25 | 50.20.0000 |  | 2026-08-03 | 50.60.0000 |  | 2026-09-28 | 60.55.0000 |  | 2026-10-26 | 60.60.0000 |  | 2026-11-23
CEN/TC 477 | SIS | 00477001 | 83050 |  | Information on mineral and metal raw materials processing schemes with consideration to European policies and regulations | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-11-21 | 2025-11-21 | 30.99.0979 |  | 2026-09-11 | [9 empty] | 50.20.0000 |  | 2026-10-16 | 50.60.0000 |  | 2027-01-08 | 60.55.0000 |  | 2027-01-22 | 60.60.0000 |  | 2027-02-05 | 2025-11-24: OSD
CEN/TC 224 | AFNOR | 00224288 | 81586 |  | Personal identification — Requirements for biometric products — Part 4: Fingerprint biometrics | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-11-20 | 2025-11-20 | 30.99.0979 |  | 2026-11-18 | [9 empty] | 50.20.0000 |  | 2027-02-17 | 50.60.0000 |  | 2027-05-12 | 60.55.0000 |  | 2027-06-09 | 60.60.0000 |  | 2027-07-07 | 2025-04-02: OSD
CEN/TC 247 | SNV | 00247144 | 81313 | prCEN/TR XXX | Proactive buildings - Integrating adaptive design and intelligent operations | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-01-21 | 2025-01-21 | 30.99.0979 |  | 2026-01-21 | [9 empty] | 50.20.0000 |  | 2026-02-25 | 50.60.0000 |  | 2026-05-20 | 60.55.0000 |  | 2026-06-03 | 60.60.0000 |  | 2026-06-17 | 2025-02-04: OSD
CEN/CLC/JTC 21 | DS | JT021029 | 79708 | prEN 18282 | Artificial intelligence - Cybersecurity specifications for AI Systems | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-10-02 | 2024-10-02 | 30.99.0979 |  | 2025-08-31 | 40.20.0000 |  | 2025-12-01 | 40.60.0000 |  | 2026-02-23 | 45.99.0979 |  | 2026-07-15 | 50.20.0000 |  | 2026-09-23 | 50.60.0000 |  | 2026-11-18 | 60.55.0000 |  | 2026-12-16 | 60.60.0000 |  | 2027-01-13 | OSD
CEN/TC 107 | DS | 00107100 | 81193 | FprCEN/TR 18341 | District heating and cooling systems - Supplementary information on usage of CEN/TC 107 documents | Submission to Vote on TR | 50.20.0000 | Homegrown | 10.99.0000 | 2025-01-08 | 2025-01-08 | 30.99.0979 | 2026-01-12 | 2026-01-12 | [9 empty] | 50.20.0000 | 2026-02-05 | 2026-02-05 | 50.60.0000 |  | 2026-04-30 | 60.55.0000 |  | 2026-05-15 | 60.60.0000 |  | 2026-05-29 | 2025-01-22:OSD
CEN/TC 158 | SIS | 00158123 | 82529 | prCEN/TR 16148 rev | Head impact and burn injury criteria - A Guide for CEN helmet standards committees | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-25 | 2025-08-25 | 30.99.0979 |  | 2026-08-18 | [9 empty] | 50.20.0000 |  | 2026-09-22 | 50.60.0000 |  | 2026-12-15 | 60.55.0000 |  | 2027-01-04 | 60.60.0000 |  | 2027-01-18 | 2025-09-12:OSD
CEN/TC 275 | DIN | 00275384 | 80388 | prEN 16802 rev | Foodstuffs - Determination of elements and their chemical species - Determination of arsenic species in foodstuffs by anion-exchange HPLC-ICP-MS | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-14 | 2025-08-14 | 30.99.0979 |  | 2026-10-22 | 40.20.0000 |  | 2027-01-21 | 40.60.0000 |  | 2027-04-15 | 45.99.0979 |  | 2027-05-27 | 50.20.0000 |  | 2027-08-05 | 50.60.0000 |  | 2027-09-30 | 60.55.0000 |  | 2027-10-28 | 60.60.0000 |  | 2027-11-25 | OSD
CEN/TC 256 | DIN | 00256A5M | 82307 | prEN 16891 rev | EN 16891, Railway applications - Acoustics - Measurement method for combined roughness, track decay rates and transfer functions | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-07-11 | 2025-07-11 | 30.99.0979 |  | 2026-03-06 | 40.20.0000 |  | 2026-06-05 | 40.60.0000 |  | 2026-08-28 | 45.99.0979 |  | 2027-04-23 | 50.20.0000 |  | 2027-07-02 | 50.60.0000 |  | 2027-08-27 | 60.55.0000 |  | 2027-09-24 | 60.60.0000 |  | 2027-10-22 | 2025-07-17:OSD
CEN/CLC/JTC 21 | DS | JT021047 | 82493 | prEN 18229-2 | AI trustworthiness framework - Part 2: Accuracy and robustness | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-05-15 | 2025-05-15 | 30.99.0979 |  | 2026-05-05 | 40.20.0000 |  | 2026-08-04 | 40.60.0000 |  | 2026-10-27 | 45.99.0979 |  | 2027-06-22 | 50.20.0000 |  | 2027-08-31 | 50.60.0000 |  | 2027-10-26 | 60.55.0000 |  | 2027-11-23 | 60.60.0000 |  | 2027-12-21 | OSD
CEN/TC 224 | AFNOR | 00224278 | 77619 | FprCEN/TS 18212-2 | Personal identification - Requirements for biometric products - Part 2: Interoperability tests | Closure of Vote on TS | 50.60.0000 | Homegrown | 10.99.0000 | 2024-11-13 | 2024-11-13 | 30.99.0979 | 2025-04-24 | 2025-04-24 | [9 empty] | 50.20.0000 | 2025-11-27 | 2025-11-27 | 50.60.0000 | 2026-02-19 | 2026-02-19 | 60.55.0000 |  | 2026-03-20 | 60.60.0000 |  | 2026-04-22 | OSD
CEN/TC 467 | UNI | 00467009 | 81435 | prCEN/TR XXX | Adaptation to climate change - Guidelines on using climate data in infrastructure standards | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-02-14 | 2025-02-14 | 30.99.0979 |  | 2026-02-26 | [9 empty] | 50.20.0000 |  | 2026-04-02 | 50.60.0000 |  | 2026-06-25 | 60.55.0000 |  | 2026-07-09 | 60.60.0000 |  | 2026-07-23 | 2025-02-18: OSD
CEN/CLC/JTC 13 | DIN | JT013100 | 82553 | prCEN/CLC/TR XXX | Proof-of-concept for the application of EN 18037 in support of the CRA | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-28 | 2025-08-28 | 30.99.0979 |  | 2026-05-15 | [9 empty] | 50.20.0000 |  | 2026-06-19 | 50.60.0000 |  | 2026-09-11 | 60.55.0000 |  | 2026-09-25 | 60.60.0000 |  | 2026-10-09 | 2025-10-31:OSD
CEN/TC 234 | DIN | 00234119 | 83105 |  | Gas infrastructure - Quality of gas - Aspects of rate of change of gas quality parameter on gas infrastructure and end-use | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-12-01 | 2025-12-01 | 30.99.0979 |  | 2026-11-03 | [9 empty] | 50.20.0000 |  | 2026-12-08 | 50.60.0000 |  | 2027-03-02 | 60.55.0000 |  | 2027-03-16 | 60.60.0000 |  | 2027-03-30 | 2025-12-16: OSD
CEN/TC 256 | DIN | 00256A4R | 80204 |  | Railway applications - Wheel/Rail Friction Management – Part 3: Rationale for requirements and further background information | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-06-18 | 2024-06-18 | 30.99.0979 |  | 2026-03-17 | [9 empty] | 50.20.0000 |  | 2026-04-21 | 50.60.0000 |  | 2026-07-14 | 60.55.0000 |  | 2026-07-28 | 60.60.0000 |  | 2026-08-11 | OSD
CEN/TC 261 | AFNOR | 00261535 | 81847 |  | Packaging — Design for recycling — Part 1: Process and design criteria to evaluate the recyclability of paper and cardboard packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 202/04/28:OSD
CEN/TC 468 | AFNOR | 00468003 | 83060 | prCEN/TS 18170 rev | Functional requirements for the electronic archiving services | Decision on WI Proposal | 10.99.0000 | Modified | 10.99.0000 | 2025-11-24 | 2025-11-24 | 30.99.0979 |  | 2026-06-01 | [9 empty] | 50.20.0000 |  | 2026-08-31 | 50.60.0000 |  | 2026-11-23 | 60.55.0000 |  | 2026-12-21 | 60.60.0000 |  | 2027-01-18 | 2025-12-10: OSD
CEN/TC 459/SC 9 | AFNOR | EC109094 | 76270 | prEN 10143 rev | Continuously hot-dip coated steel sheet and strip - Tolerances on dimensions and shape | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-19 | 2025-09-19 | 30.99.0979 |  | 2026-05-15 | 40.20.0000 |  | 2026-08-14 | 40.60.0000 |  | 2026-11-06 | 45.99.0979 |  | 2027-07-02 | 50.20.0000 |  | 2027-09-10 | 50.60.0000 |  | 2027-11-05 | 60.55.0000 |  | 2027-12-03 | 60.60.0000 |  | 2028-01-03 | 2025-03-13: OSD
CEN/TC 143 | SNV | 00143106 | 82167 | prEN 13236 rev | Safety requirements for superabrasive products | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-06-17 | 2025-06-17 | 30.99.0979 |  | 2026-02-10 | 40.20.0000 |  | 2026-05-12 | 40.60.0000 |  | 2026-08-04 | 45.99.0979 |  | 2027-03-30 | 50.20.0000 |  | 2027-06-08 | 50.60.0000 |  | 2027-08-03 | 60.55.0000 |  | 2027-08-31 | 60.60.0000 |  | 2027-09-28 | 2025-06-26:OSD
CEN/CLC/JTC 22 | DIN | JT022012 | 82296 | prEN XXX | Characterization methods for ion traps used in quantum computing and sensing | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-06-11 | 2025-06-11 | 30.99.0979 |  | 2026-02-04 | 40.20.0000 |  | 2026-05-06 | 40.60.0000 |  | 2026-07-29 | 45.99.0979 |  | 2027-03-24 | 50.20.0000 |  | 2027-06-02 | 50.60.0000 |  | 2027-07-28 | 60.55.0000 |  | 2027-08-25 | 60.60.0000 |  | 2027-09-22 | 2025-07-10:OSD
CEN/CLC/JTC 21 | DS | JT021025 | 79657 | prEN 18281 | Artificial Intelligence - Evaluation methods for accurate computer vision systems | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-11-20 | 2024-11-20 | 30.99.0979 |  | 2026-03-31 | 40.20.0000 |  | 2026-06-30 | 40.60.0000 |  | 2026-09-22 | 45.99.0979 |  | 2026-09-02 | 50.20.0000 |  | 2026-11-12 | 50.60.0000 |  | 2027-01-07 | 60.55.0000 |  | 2027-02-04 | 60.60.0000 |  | 2027-03-04 | OSD
CEN/TC 169 | DIN | 00169107 | 83521 |  | CEN/TS 12464-3: Light and Lighting – Lighting of work places – Part 3: Non-visual effects of lighting | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-20 | 2026-02-20 | 30.99.0979 |  | 2028-02-15 | [9 empty] | 50.20.0000 |  | 2028-05-16 | 50.60.0000 |  | 2028-08-08 | 60.55.0000 |  | 2028-09-05 | 60.60.0000 |  | 2028-10-03 | OSD
CEN/TC 107 | DS | 00107099 | 81183 | prEN 17248 | District heating and district cooling pipe systems - Terms and definitions | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2025-01-02 | 2025-01-02 | 30.99.0979 | 2025-10-29 | 2025-10-29 | 40.20.0000 | 2026-01-15 | 2026-01-15 | 40.60.0000 |  | 2026-04-09 | 45.99.0979 |  | 2026-10-15 | 50.20.0000 |  | 2026-12-24 | 50.60.0000 |  | 2027-02-18 | 60.55.0000 |  | 2027-03-18 | 60.60.0000 |  | 2027-04-15 | 2025-02-26: OSD
CEN/CLC/JTC 21 | DS | JT021019 | 78133 | prEN 18274 | Competence requirements for professional AI ethicists | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-06-19 | 2024-06-19 | 30.99.0979 | 2025-09-10 | 2025-09-10 | 40.20.0000 | 2025-09-18 | 2025-09-18 | 40.60.0000 | 2025-12-11 | 2025-12-11 | 45.99.0979 |  | 2027-01-01 | 50.20.0000 |  | 2027-03-12 | 50.60.0000 |  | 2027-05-07 | 60.55.0000 |  | 2027-06-04 | 60.60.0000 |  | 2027-07-02 | OSD 2025-05-22 KG : WI title modified following TC decsiion 10 on 2025-05-15 2024-05-15: WI justification too big & didn't fit in field, last bullet missing: "- the applicability and benefits of implementing the standard across various sectors and contexts"
CEN/TC 440 | DIN | 00440033 | 83405 |  | Electronic Public Procurement – Fulfilment – Part 3-1: Syntax Binding, UBL | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-01-30 | 2026-01-30 | 30.99.0979 |  | 2027-02-09 | [9 empty] | 50.20.0000 |  | 2027-05-11 | 50.60.0000 |  | 2027-08-03 | 60.55.0000 |  | 2027-08-31 | 60.60.0000 |  | 2027-09-28 | 2026-02-03-OSD
CEN/CLC/JTC 13 | DIN | JT013099 | 82552 | prCEN/CLC/TS XXX | Guidance for the application of EN 18037 in support of the CRA | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-28 | 2025-08-28 | 30.99.0979 |  | 2026-05-15 | [9 empty] | 50.20.0000 |  | 2026-08-14 | 50.60.0000 |  | 2026-11-06 | 60.55.0000 |  | 2026-12-04 | 60.60.0000 |  | 2027-01-04 | 2025-10-31:OSD
CEN/TC 156 | BSI | 00156301 | 79757 | prEN 18289 | Ventilation for buildings - Metallic ventilation ducts - Requirements and test methods | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-03-21 | 2024-03-21 | 30.99.0979 | 2025-10-06 | 2025-10-06 | 40.20.0000 | 2026-01-29 | 2026-01-29 | 40.60.0000 |  | 2026-04-23 | 45.99.0979 |  | 2026-10-01 | 50.20.0000 |  | 2026-12-10 | 50.60.0000 |  | 2027-02-04 | 60.55.0000 |  | 2027-03-04 | 60.60.0000 |  | 2027-04-01 | 2025-04-07: OSD
CEN/CLC/JTC 22 | DIN | JT022015 | 82414 | prCEN/CLC/TR XXX | Design aspects of quantum communication networks | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-07-24 | 2025-07-24 | 30.99.0979 |  | 2026-09-01 | [9 empty] | 50.20.0000 |  | 2026-10-06 | 50.60.0000 |  | 2027-01-04 | 60.55.0000 |  | 2027-01-18 | 60.60.0000 |  | 2027-02-01 | 2025-08-05: OSD
CEN/TC 264 | DIN | 00264255 | 81988 |  | Stationary source emissions – Diffuse emissions measurement methods – Overview of standards and other documents | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-05-14 | 2025-05-14 | 30.99.0979 |  | 2026-07-31 | [9 empty] | 50.20.0000 |  | 2026-09-04 | 50.60.0000 |  | 2026-11-27 | 60.55.0000 |  | 2026-12-11 | 60.60.0000 |  | 2027-01-04
CEN/TC 250 | BSI | 00250295 | 82038 | prCEN/TS 1995-1-101 | Eurocode 5 - Design of timber structures - Part 1-101: Design assisted by numerical methods | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-05-27 | 2025-05-27 | 30.99.0979 |  | 2026-05-27 | [9 empty] | 50.20.0000 |  | 2026-08-26 | 50.60.0000 |  | 2026-11-18 | 60.55.0000 |  | 2026-12-16 | 60.60.0000 |  | 2027-01-13 | 2025-06-12: OSD
CEN/TC 460 | DIN | 00460023 | 79971 | prEN 18179 | Food authenticity - Method for detecting previously frozen poultry meat by determination of HADH activity | Acceptance of FV draft | 45.99.0979 | Homegrown | 10.99.0000 | 2024-04-29 | 2024-04-29 | 30.99.0979 | 2025-01-17 | 2025-01-17 12:14 | 40.20.0000 | 2025-04-17 | 2025-04-17 | 40.60.0000 | 2025-07-10 | 2025-07-10 | 45.99.0979 | 2026-02-19 | 2026-02-19 | 50.20.0000 |  | 2026-04-23 | 50.60.0000 |  | 2026-06-18 | 60.55.0000 |  | 2026-07-16 | 60.60.0000 |  | 2026-08-13 | OSD
CEN/TC 107 | DS | 00107098 | 81137 |  | Development of energy system-integration | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-01 | 2025-10-01 | 30.99.0979 |  | 2026-10-31 | [9 empty] | 50.20.0000 |  | 2026-12-07 | 50.60.0000 |  | 2027-03-01 | 60.55.0000 |  | 2027-03-15 | 60.60.0000 |  | 2027-03-29 | 2025-10-13: OSD
CEN/TC 256 | DIN | 00256A2O | 76296 | prEN 17833 | Railway applications - Simulation Credibility | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2025-06-25 | 2025-06-25 | 30.99.0979 | 2025-12-01 | 2025-12-01 | 40.20.0000 | 2026-01-15 | 2026-01-15 | 40.60.0000 |  | 2026-04-09 | 45.99.0979 |  | 2027-04-07 | 50.20.0000 |  | 2027-06-16 | 50.60.0000 |  | 2027-08-11 | 60.55.0000 |  | 2027-09-08 | 60.60.0000 |  | 2027-10-06 | OSD
CEN/TC 261 | AFNOR | 00261538 | 81850 |  | Packaging — Design for recycling — Part 2: Testing protocol for glass packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 202/04/28:OSD
CEN/TC 143 | SNV | 00143107 | 82910 | prEN 12413 rev | Safety requirements for bonded abrasive products | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-21 | 2025-10-21 | 30.99.0979 |  | 2026-06-16 | 40.20.0000 |  | 2026-09-15 | 40.60.0000 |  | 2026-12-08 | 45.99.0979 |  | 2027-08-03 | 50.20.0000 |  | 2027-10-12 | 50.60.0000 |  | 2027-12-07 | 60.55.0000 |  | 2028-01-04 | 60.60.0000 |  | 2028-02-01 | 2025-11-13: OSD
CEN/TC 366 | UNI | 00366023 | 82612 | prCEN/TS 17045 rev | Materials obtained from end-of-life tyres - Quality criteria for the selection of whole tyres, for recovery and recycling processes | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-10 | 2025-09-10 | 30.99.0979 |  | 2026-09-10 | [9 empty] | 50.20.0000 |  | 2026-12-10 | 50.60.0000 |  | 2027-03-04 | 60.55.0000 |  | 2027-04-01 | 60.60.0000 |  | 2027-04-29 | OSD
CEN/TC 261 | AFNOR | 00261543 | 82000 |  | Packaging — Design for recycling — Part 1: Definitions and general principles of the process and design criteria to evaluate the recyclability of packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-05-16 | 2025-05-16 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 2025-05-20:OSD
CEN/TC 256 | DIN | 00256A4X | 80607 |  | Railway applications - Pressure gauges | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2026-02-02 | 2026-02-02 | 30.99.0979 |  | 2026-09-28 | 40.20.0000 |  | 2027-01-04 | 40.60.0000 |  | 2027-03-29 | 45.99.0979 |  | 2027-11-15 | 50.20.0000 |  | 2028-01-24 | 50.60.0000 |  | 2028-03-20 | 60.55.0000 |  | 2028-04-17 | 60.60.0000 |  | 2028-05-15 | OSD
CEN/TC 248 | BSI | 00248801 | 82127 |  | Smart textiles and electronic textiles — Textile products with active lighting — Determination of the luminance | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-06-06 | 2025-06-06 | 30.99.0979 |  | 2026-04-30 | 40.20.0000 |  | 2026-07-30 | 40.60.0000 |  | 2026-10-22 | 45.99.0979 |  | 2027-03-19 | 50.20.0000 |  | 2027-05-28 | 50.60.0000 |  | 2027-07-23 | 60.55.0000 |  | 2027-08-20 | 60.60.0000 |  | 2027-09-17 | 2025-10-07:OSD